## Sheet1
Sno | Client | WORK DESCRIPTION | Allocated Time | Allocated Person | Closing Time | Status | Required Hrs | Completed Hrs | Remarks
1 | Mbar_rambabar | 1. Unable to add new user 2. unable to add new usergroup 3. Unable to give user grp rights |  |  |  | Completed |  |  | Api calling is pending
2 | Lepalace | Today created a new web page for hotelepalace |  |  |  | Completed |  |  | tomorrow check and update to server

## Sheet2
|  | Sno | Client | WORK DESCRIPTION | Allocated Time | Allocated Person | Closing Time | Status | Required Hrs | completed Hrs | Remarks
Sno | Client | WORK DESCRIPTION | [6 empty] | Allocated Time |  | Allocated Person | Closing Time | Status | Required Hrs | Completed Hrs | Remarks
1 | Lepalace | Today created a new web page for hotelepalace | [10 empty] | Completed |  |  | tomorrow check and update to server

## Sheet3
Sno | Client | WORK DESCRIPTION | Allocated Time | Allocated Person | Closing Time | Status | Required Hrs | Completed Hrs | Remarks
1 | Lepalace | Today all the images are converted and uploaded in cloud and use it |  |  |  | Completed |  |  | Tested and uploaded in the server.
2 | Sherlock | Today solved the issues in billprint |  |  |  | Completed |  |  | Testing pending

## Sheet4
Sno | Client | WORK DESCRIPTION |  | Allocated Time | Allocated Person | Closing Time | Status | Required Hrs | Completed Hrs | Remarks
1 | Rambabar | menu rights and alignment |  |  |  |  | Completed |  |  |  | menu issuse solved
2 | sherlock |  | nckot billbrint came two times same item |  |  |  | Completed
Solved

## Sheet5
Sno | Client | WORK DESCRIPTION |  | Allocated Time | Allocated Person | Closing Time | Status | Required Hrs | Completed Hrs | Remarks
1 | Rambabar | suppress zero task |  |  | padmanaban | 12:00 | Completed |  | 3hrs |  | solved
2 | Rambabar |  | add filter option for item group |  |  |  | Completed
[5 empty] | padmanaban | 6:45pm |  | 5hrs | 5hrs |  | Solved

## Sheet6
Sno | Client | WORK DESCRIPTION | Allocated Time | Allocated Person | Closing Time | Status | Required Hrs | Completed Hrs | Remarks
1 | Rambabar | Store Stock Report - Need item groupwise List. Need filter for Specific Item or specific Group & Sub group | 10:00AM | Padmanaban | 6:30pm | Completed | 8 1/2 hrs | 6hrs | solved
2 | Rambabar | Bar Stock Report - Need item groupwise List. Need filter for Specific Item or specific Group & Sub group | 7:30AM | Padmanaban | 8:30pm | Completed | 1hrs | 1hrs | solved
3 | Rambabar | Stock Opening - Qty - allowing only 3 digit | 9:30pm | Padmanaban | 9:35pm | Completed | 5min | 5min | solved
4 | Rambabar | Stock Opening - Food Items are coming | 9:40pm | Padmanaban | 10:10pm | Completed | 5min | 30min | solved

## Sheet7
Sno | Client | WORK DESCRIPTION | Allocated Time | Allocated Person | Closing Time | Status | Required Hrs | Completed Hrs | Remarks
1 | Rambabar | inward ,purchase_list and adjustment page save button issue when popup. | 10:00AM | Naveen | 12:30pm | Completed | 2 1/2 hrs | 2 1/2hrs | solved
2 | Rambabar | In bill print Change the phone number | 4:00pM | Naveen | 4:10pm | Completed | 10 min | 10 min | solved
3 | Rambabar | Order issuse in kot and kot save error msg showing | 4:30pM | Naveen | 5:00pm | Completed | 30 min | 30 min | solved
4 | Kasisinn | Occupancy report alignment and remove print and pdf | 5:00pM | Naveen | 6:30pm | Completed | 1 1/2 hrs | 1 1/2 hrs | Completed

## Sheet8
Sno | Client | WORK DESCRIPTION | Allocated Time | Allocated Person | Closing Time | Status | Required Hrs | Completed Hrs | Remarks
1 | Kasisinn | Night audit not working when room are occupied | 10:00AM | Arun | 12:30pm | Completed | 2 1/2 hrs | 2 1/2hrs | solved
2 | Kasisinn | Occupany List Rework | 4:00pM | Arun | 6:30pm | Completed | 2 1/2 hrs | 2 1/2 hrs | solved

## 20-06-2025
Sno | Client | WORK DESCRIPTION | Allocated Time | Allocated Person | Closing Time | Status | Required Hrs | Completed Hrs | Remarks
1 | Brindavan | 1. API End point Create for two endpoints | 9:40 | Arun | 06:30pm | Working | 7 hrs | 7 hrs | Created two endpoints
2.Created the database for user and url storing.
3. Retrive the datas from table and post into the tables
2 | Kasisinn | Postrent Bug | 6:45 | Padmanaban | 06:55pm | Completed | 10 mins | 10 mins | Solved the postrent button bug
Work Schedule on Tomorrow
Sno | Client | WORK DESCRIPTION | No.Of Working Hours
1 | Brindavan | API end point creating for other endpoints | 6 days

## 21-06-2025
Sno | Client | WORK DESCRIPTION | Allocated Time | Allocated Person | Closing Time | Status | Required Hrs | Completed Hrs | Remarks
1 | Brindavan | API creation creating one end point for token genration | 9:40 | Arun | 10:30 | Working | 50 mins | 50 mins | Created two endpoints
2 | kasisinn | change company column in the occupancy report list | 10:30 | Padmanaban | 10:35 | Completed | 5 mins | 5 mins | Testing required
3 | kasisinn | Given Header for the Inhouse list | 10:35 | Padmanaban | 10:45 | Completed | 10 mins | 10 mins | Testing required
4 | kasisinn | Checkout list is showing in Inhouse | 10:45 | Padmanaban | 11:20 | Completed | 35 mins | 35 mins | Testing required
5 | kasisinn | In Cashier report showing same receipt number multiple times | 11:20 | Padmanaban | 12:00 | Completed | 40 mins | 40 mins | Testing required
6 | kasisinn | Today checkin,Today Checkout coolumns in occupancy corrections | 12:00 | Padmanaban | 12:30 | Completed | 30 mins | 30 mins | Testing required
7 | Meeting | Attended Meeting with senthil sir | 12:30 | senthil sir | 14:30 | Completed | 1 hrs 30 mins | 1 hrs 30 mins | Meeting Completed
8 | Shutdown | Today Shutdown , So system have no power | 14:30 | senthil sir | 17:00 | Shutdown | 2 hrs 30 mins | 2 hrs 30 mins | Shutdown
9 | kasisinn | In Reservation form error correction | 17:00 | Arun | 17:20 | Completed | 20 mins | 20 mins | Testing
10 | kasisinn | Checkin screen bug fixing | 17:20 | Arun | 18:30 | Inprogress | 50 mins | 50 mins | Pending
Work Schedule on Tomorrow
Sno | Client | WORK DESCRIPTION | No.Of Working Hours
1 | Kasisinn | All form and Report bugs | 3 days

## 23-06-2025
Sno | Client | WORK DESCRIPTION | Allocated Time | Allocated Person | Closing Time | Status | Required Hrs | Completed Hrs | Remarks
1 | Brindavan | API creation creating one end point for checkin | 9:40 | Arun | 10:30 | Working | 50 mins | 50 mins | Created the endpoints
2 | Hotel Le Royal | Analysing the demo website | 10:30 | Padmanaban | 11:00 | Completed | 30 mins | 30 mins | Analysed
3 | Hotel Le Royal | Creating the website structure and Naming the pages | 11:00 | Padmanaban | 11:45 | Completed | 45 mins | 45 mins | Completed
4 | Hotel Le Royal | Creating the Index page with all of the sections | 11:45 | Padmanaban | 13:45 | Completed | 2 hrs | 2 hrs | Completed
5 | Hotel Le Royal | Converting the logo images to png | 13:45 | Padmanaban | 14:00 | Completed | 15 mins | 15 mins | Completed
6 | Hotel Le Royal | Creating the Rooms section with content and transition | 14:40 | Padmanaban | 16:30 | Completed | 1 hr 50 mins | 1 hr 50 mins | Completed
7 | Hotel Le Royal | Creating the Footer section with attrative | 16:30 | Padmanaban | 18:45 | Completed | 2 hr 15 mins | 2 hr 15 mins | Completed
Work Schedule on Tomorrow
Sno | Client | WORK DESCRIPTION | No.Of Working Hours
1 | Hotel Le Royal | Create Other pages with the contents | 1 1/2 day

## 24-06-2025
Sno | Client | WORK DESCRIPTION | Allocated Time | Allocated Person | Closing Time | Status | Required Hrs | Completed Hrs | Remarks
1 | Le Royal Suite | creating the about page | 9:40 | Arun | 10:30 | Completed | 50 mins | 50 mins | completed
2 | Le Royal Suite | creating a gallery section in index page | 10:30 | Arun | 10:50 | completed | 20 mins | 20 mins | completed
3 | Le Royal Suite | creating Slideshow for gallery | 10:50 | Arun | 12:50 | completed | 2 hrs | 2 hrs | completed
4 | Le Royal Suite | creating a gallery section in About page | 12:50 | Arun | 14:00 | completed | 1hr 10 mins | 1hr 10 mins | completed
5 | Le Royal Suite | creating aintro section in index page | 14:45 | Arun | 15:45 | completed | 1hr | 1hr | completed
6 | Le Royal Suite | creating contact page with forms | 15:45 | Arun | 17:15 | completed | 1hr 30 mins | 1hr 30 mins | completed
7 | Lalitha Mahal | bug in login form | 17:15 | Arun | 17:45 | completed | 30 mins | 30 mins | completed
8 | Le Royal Suite | request and confirmation photos to client | 17:45 | Arun | 18:45 | completed | 1 hrs | 1 hrs | completed
Work Schedule on Tomorrow
Sno | Client | WORK DESCRIPTION | No.Of Working Hours
1 | Brindhavan | create other API | 3 days

## 25-06-2025
Sno | Client | WORK DESCRIPTION | Allocated Time | Allocated Person | Closing Time | Status | Required Hrs | Completed Hrs | Remarks
1 | Le Royal Suite | creating the about page | 9:40 | Arun | 10:30 | Completed | 50 mins | 50 mins | completed
2 | Le Royal Suite | creating a gallery section in index page | 10:30 | Arun | 10:50 | completed | 20 mins | 20 mins | completed
3 | Le Royal Suite | creating Slideshow for gallery | 10:50 | Arun | 12:50 | completed | 2 hrs | 2 hrs | completed
4 | Le Royal Suite | creating a gallery section in About page | 12:50 | Arun | 14:00 | completed | 1hr 10 mins | 1hr 10 mins | completed
5 | Le Royal Suite | creating aintro section in index page | 14:45 | Arun | 15:45 | completed | 1hr | 1hr | completed
6 | Le Royal Suite | creating contact page with forms | 15:45 | Arun | 17:15 | completed | 1hr 30 mins | 1hr 30 mins | completed
7 | Lalitha Mahal | Changing styles and fonts | 17:15 | Arun | 17:45 | completed | 30 mins | 30 mins | completed
8 | Le Royal Suite | Alignmenting all the text | 17:45 | Arun | 18:45 | completed | 1 hrs | 1 hrs | completed
9 | Le Royal Suite | Deploying in the server | 18:45 | Arun | 19:15 | completed | 30 mins | 30 mins | completed
Work Schedule on Tomorrow
Sno | Client | WORK DESCRIPTION | No.Of Working Hours
1 | Brindhavan | create other API | 2 days

## 26-06-2025
Sno | Client | WORK DESCRIPTION | Allocated Time | Allocated Person | Closing Time | Status | Required Hrs | Completed Hrs | Remarks
1 | Le Royal Suite | creating the near by distance section | 9:40 | Arun | 11:40 | Completed | 2 hrs | 2 hrs | completed
2 | Le Royal Suite | Alignmenting the text and resizing the Images | 11:40 | Arun | 12:40 | completed | 1 hrs | 1 hrs | completed
3 | Le Royal Suite | Creating Account in email.js and setup | 12:40 | Arun | 13:00 | completed | 20 mins | 20 mins | completed
4 | Le Royal Suite | Creating email template and public keys | 13:00 | Arun | 14:00 | completed | 1hr | 1hr | completed
5 | Le Royal Suite | Updating website in server | 14:40 | Arun | 15:30 | completed | 50 mins | 50 mins | completed
6 | Brindhavan | Creating Checkin Api | 15:30 | Arun | 16:30 | completed | 1 hr | 1 hr | completed
7 | Brindhavan | Creating Checkout Api and group checkin | 16:30 | Arun | 17:30 | completed | 1 hr | 1 hr | completed
8 | Brindhavan | Creating group Checkout Api and Housekeeping | 15:30 | Arun | 16:30 | completed | 1 hr | 1 hr | completed
Work Schedule on Tomorrow
Sno | Client | WORK DESCRIPTION | No.Of Working Hours
1 | Brindhavan | Testing for brindhavan Api's | 1 day

## 27-06-2025
Sno | Client | WORK DESCRIPTION | Allocated Time | Allocated Person | Closing Time | Status | Required Hrs | Completed Hrs | Remarks
1 | Brindhavan | Testing api in local | 9:40 | Arun | 13:40 | Completed | 4 hrs | 4 hrs | completed
2 | Le Royal Suite | Creating the map in the website | 14:10 | Arun | 14:40 | completed | 30 mins | 30 mins | completed
3 | Kasisinn | Checking the screens | 14:40 | Arun | 18:40 | completed | 4 hrs | 4 hrs | completed
Work Schedule on Tomorrow
Sno | Client | WORK DESCRIPTION | No.Of Working Hours
1 | Brindhavan | Testing for brindhavan Api's for client side | 1 day

## 28-06-2025
Sno | Client | WORK DESCRIPTION | Allocated Time | Allocated Person | Closing Time | Status | Required Hrs | Completed Hrs | Remarks
1 | Brindhavan | Testing api in local | 9:40 | Arun | 10:40 | Completed | 1 hrs | 1 hrs | completed
2 | Nitheesresidency | working in IRM website | 10:40 | Arun | 13:40 | Pending | 3 hrs | 3 hrs | pending
3 | Rambabar | Clearing all errors in rambabar | 14:20 | Arun | 15:40 | completed | 1 hr 20 mins | 1 hr 20 mins | completed
4 | kasisinn | Checking the screens in all kasisinn frontoffice | 15:40 | Arun | 18:40 | completed | 3 hrs | 3 hrs | completed
Work Schedule on Tomorrow
Sno | Client | WORK DESCRIPTION | No.Of Working Hours
1 | Brindhavan | Testing for brindhavan Api's for (client side pending) | 1 day

## 30-06-2025
Sno | Client | WORK DESCRIPTION | Allocated Time | Allocated Person | Closing Time | Status | Required Hrs | Completed Hrs | Remarks
1 | Brindhavan | Testing api in client side | 9:40 | Arun | 11:40 | Pending | 2 hrs | 2 hrs | Pending
2 | Kasisinn | checking and clearing errors | 11:40 | Arun | 13:40 | Pending | 2 hrs | 2 hrs | pending
3 | Microgenn | Website source checking for content change | 14:20 | Arun | 15:20 | Pending | 1 hrs | 1 hrs | pending
4 | Brindhavan | Testing api in client side | 15:20 | Arun | 17:20 | partial completed | 2 hrs | 2 hrs | partial completed
5 | Kasisinn | checking and clearing errors | 17:20 | Arun | 18:40 | Completed | 1 hr 20 mins | 1 hr 20 mins | Completed
Work Schedule on Tomorrow
Sno | Client | WORK DESCRIPTION | No.Of Working Hours
1 | Brindhavan | Testing for brindhavan Api's for (client side pending) | 1 day

## 01-07-2025
Sno | Client | WORK DESCRIPTION | Allocated Time | Allocated Person | Closing Time | Status | Required Hrs | Completed Hrs | Remarks
1 | Brindhavan | Testing api in client side | 9:40 | Arun | 10:00 | Pending | 20 mins | 20 mins | Pending
2 | Kasisinn | Clearing bug In settlement screen | 10:00 | Arun | 11:30 | Completed | 1 hr 30 mins | 1 hr 30 mins | Completed
3 | Kasisinn | Changing paymode id to paymode name in advancesettlement screen | 11:30 | Arun | 12:00 | Completed | 30 mins | 30 mins | Completed
4 | Kasisinn | Changing paymode id to paymode name in resettlement screen | 12:00 | Arun | 12:30 | Completed | 30 mins | 30 mins | partial completed
5 | Leroyalsuite | Creating google business id for leroyalsuite | 12:30 | Senthil | 13:00 | pending | 30 mins | 30 mins | Mail id asked to client
6 | Kasisinn | Checking guest amendment screen | 13:30 | Arun | 14:00 | Completed | 30 mins | 30 mins | Completed
7 | Kasisinn | Checking room transfer screen | 14:30 | Arun | 15:00 | Completed | 30 mins | 30 mins | Completed
8 | Kasisinn | Checking checkout resettlement screen | 15:00 | Arun | 16:00 | Completed | 1 hr | 1 hr | Completed
9 | Kasisinn | Checking Advance resettlement screen | 16:00 | Arun | 17:00 | Completed | 1 hr | 1 hr | Completed
10 | Kasisinn | Checking settlement save screen and clearing bugs | 17:00 | Arun | 18:40 | Completed | 1 hr 40 mins | 1 hr 40 mins | Completed
Work Schedule on Tomorrow
Sno | Client | WORK DESCRIPTION | No.Of Working Hours
1 | Brindhavan | Testing for brindhavan Api's for (client side pending) | 1 day
2 | Kasisinn | Day book,tooroom,reports screens are pending | 1 day
3 | Nitheesresidency | IRM booking requirement pending | Analysing

## 02-07-2025
Sno | Client | WORK DESCRIPTION | Allocated Time | Allocated Person | Closing Time | Status | Required Hrs | Completed Hrs | Remarks
1 | Brindhavan | Testing api in client side | 9:40 | Arun | 12:00 | Completed | 2hrs 30mins | 2hrs 30mins | Completed
2 | Kasisinn | Clearing bug In settlement screen | 12:00 | Arun | 14:30 | Completed | 2 hrs | 2 hrs | Completed
3 | Kasisinn | Changing paymode id to paymode name in advancesettlement screen | 2:30 | Arun | 4:30 | Completed | 2 hrs | 2 hrs | Completed
4 | Kasisinn | Changing paymode id to paymode name in resettlement screen | 16:30 | Arun | 18:30 | Completed | 2 hrs | 2 hrs | Completed
Work Schedule on Tomorrow
Sno | Client | WORK DESCRIPTION | No.Of Working Hours
1 | Brindhavan | Testing for brindhavan Api's for (client side pending) | 1 day
2 | Kasisinn | Day book,tooroom,reports screens are pending | 1 day
3 | Nitheesresidency | IRM booking requirement pending | Analysing

## 03-07-2025
Sno | Client | WORK DESCRIPTION | Allocated Time | Allocated Person | Closing Time | Status | Required Hrs | Completed Hrs | Remarks
1 | Brindhavan | Api modification for brindavan | 9:40 | Arun | 12:00 | Completed | 2hrs 30mins | 2hrs 30mins | Completed
2 | Kasisinn | In collection changing paymode id to name | 12:00 | Arun | 14:30 | Completed | 2 hrs | 2 hrs | Completed
3 | MBAR | Checking and solving bugs in kot print | 2:30 | Arun | 3:30 | Completed | 1 hrs | 1 hrs | Completed
4 | Kasisinn | In reservation changing date insert as given requirement | 15:30 | Arun | 17:30 | Completed | 2 hrs | 2 hrs | Completed
5 | Kasisinn | ResAdvance resettlement screen checking and work on partial settlement | 17:30 | Arun | 19:00 | Completed | 1 hr 30 mins | 1 hr 30 mins | Completed
Work Schedule on Tomorrow
Sno | Client | WORK DESCRIPTION | No.Of Working Hours
1 | Brindhavan | Testing for brindhavan Api's for (client side pending) | 1 day
2 | Nitheesresidency | IRM booking requirement pending | 2 day

## 04-07-2025
Sno | Client | WORK DESCRIPTION | Allocated Time | Allocated Person | Closing Time | Status | Required Hrs | Completed Hrs | Remarks
1 | Brindhavan | Testing in client side | 9:40 | Arun | 10:40 | Completed | 1 hr | 1 hr | Completed
2 | IRM | Working in IRM | 10:40 | Arun | 14:40 | Pending | 4 hrs | 4 hrs | Pending
3 | Leroyalsuite | Creating mail and register in google business | 14:40 | Senthil | 15:30 | Completed | 1 hrs | 1 hrs | Completed
4 | Microgenn | Checking microgen files in panel | 15:30 | Arun | 16:30 | Completed | 1 hr | 1 hr | Searching in server
5 | IRM | Working In IRM | 16:30 | Arun | 19:00 | Completed | 2 hrs 30 mins | 2 hrs 30 mins | Pending
Work Schedule on Tomorrow
Sno | Client | WORK DESCRIPTION | No.Of Working Hours
1 | IRM | IRM website work | 1 day

## 05-07-2025
Sno | Client | WORK DESCRIPTION | Allocated Time | Allocated Person | Closing Time | Status | Required Hrs | Completed Hrs | Remarks
1 | IRM | config the database | 9:40 | Arun | 10:00 | Completed | 20 mins | 20 mins | Completed
2 | IRM | pointing the index | 10:00 | Arun | 14:00 | Pending | 4 hrs | 4 hrs | Completed
3 | IRM | Checking in Master | 14:40 | Arun | 15:20 | Completed | 40 mins | 40 mins | Completed
4 | IRM | Checking in uploads | 15:20 | Arun | 16:00 | Completed | 40 mins | 40 mins | Completed
5 | IRM | Checking in settings | 16:00 | Arun | 17:00 | Completed | 1 hr | 1 hr | Completed
6 | IRM | Checking in Reports | 17:00 | Arun | 18:00 | Completed | 1 hr | 1 hr | Completed
Work Schedule on Tomorrow
Sno | Client | WORK DESCRIPTION | No.Of Working Hours
1 | IRM | IRM website work | 1 day
2 | Brindhavan | Testing in client side | 1 day